## Baseline
Benefits Register 2024-25
Benefit ID | Project Name | Benefit Owner (Lead) | Benefit Name | Benefit Category | Benefit Metric Description | Strategic Alignment (Pillar 1/2/3/4/5/QIPP/BV) | Units (£ / % / hours etc) | Measurement Frequency | Data Source | Baseline Value | Target Value | Target Date | Current Value | Benefits Notes | Benefit RAG | Last Reviewed Date
B001 (Example Benefit) | Project X | Joe Bloggs | Reduction in Waiting Times | Non-Financial: Qualitative | Reduction in waiting times for a patient to be referred from secondary care currently 23 weeks, to primary care to under 4 weeks by June 2025 | 5 | Hours | Monthly | Report from S1 | 23 Weeks | 4 Weeks | 2025-06-01 | 23 Weeks |  | On Track for Achieving Target | 2023-07-01

## Definitions
Benefit Category | Description | Examples
Financial: Non-Cash Releasing (Money will be saved, but it will be spent elsewhere) | A non-cash releasing benefit refers to improvements or gains achieved by an organisation that do not directly result in an increase in available cash, however they still add value to the organisation. These benefits typically enhance operational efficiency, improve quality, or contribute to strategic goals without immediately affecting the cash flow. | Employee Satisfaction and Engagement: Initiatives that boost employee morale, satisfaction, or retention, leading to lower turnover rates and better performance, but does not directly affect the cash flow.
Financial: Cash Releasing (Money will be saved, or goes back into the bank) | A cash-releasing benefit refers to savings or financial gains that an organisation achieves, which directly result in an increase in available cash or funds. These benefits are often the outcome of initiatives or actions that reduce costs, increase efficiency, or optimise resource use, thereby freeing up cash that can be used elsewhere within the organisation. | Cost Reduction: Lowering operational costs, for example reducing overhead expenses, cutting down on waste, or negotiating better rates with suppliers. Process Efficiency: Streamlining processes to reduce the time and resources required to complete tasks, leading to lower labour costs or reduced spending on materials.
Societal (Where the wider benefit can be monetised) | A societal benefit refers to a positive impact or advantage that extends beyond an individual or organisation, contributing to the well-being of society as a whole. These benefits are often the result of actions, policies, projects, or initiatives that address social, environmental, economic, or health-related issues, thereby enhancing the quality of life, promoting equity, and fostering sustainable development within a community or broader society. | Public Health Improvements: Actions that improve public health, for example vaccination programmes, pollution reduction, or access to clean water, which contribute to healthier populations and reduce the burden on healthcare systems. Environmental Sustainability: Initiatives that protect the environment, such as reducing carbon emissions, conserving natural resources, or promoting renewable energy, which help mitigate climate change and preserve ecosystems for future generations.
Non-Financial: Qualitative (Can be measured, but not monetised) | Qualitative benefits are non-monetary advantages or improvements that result from a project, initiative, or action, and are typically measured by their impact on quality, satisfaction, perception, or experience rather than through direct financial metrics. These benefits are often intangible and harder to quantify, but they play a crucial role in assessing the overall value and success of a decision or investment. | Improved Customer Satisfaction: Enhancements that lead to better customer experiences, for example improved service quality, or more personalised interactions, which can strengthen relationships. Enhanced Employee Morale and Engagement: Actions that improve workplace culture, such as recognition programmes, better communication, or leadership development, which can lead to higher employee satisfaction, reduced turnover, and increased productivity.

## 5YFP
5 Pillars | Description
1 | Improve the lives of 100,000 people impacted by poor mental health
2 | Prevent 55,000 children from becoming overweight by 2040
3 | Reduce gap in healthy life expectancy
4 | Increase the % of older people living well and independently
5 | Add 100,000 healthy life years to the people of Dorset

## Categories (DO NOT DELETE) (hidden)
Financial: Non-Cash Releasing | On Track for Achieving Target
Financial: Cash Releasing | At Risk for Achieving Target
Societal | Benefit Off Track
Non-Financial: Qualitative | Benefit Delivered
1
2
3
4
5
QIPP
Best Value
Mandated