## Required Resources
Project Activities & Required Resources
Project Phase | Key Task | Timeframe | Effort (Time) | Activities to Achieve/Dependancies or Constraints | Deliverable(s)/Milestone | Resource Type | Cost of Resource | Notes
Planning & Design | Defining the project | 2020-01-01 | 1 week | problem definition / scope workshop / estimating costs, resource etc. Objective setting/benefits definition | Problem statement/project vision, project brief/scope document Agreement to proceed to business case | Project Manager Business Analyst | Internal existing resource - cost neutral
Planning & Design | Business case development | Jan 2020 - Jun 2020 | 6 months / 2 days per week | Refine estimates/plans Build case for change/justification | OBC / FBC / sign off | External specialist/consultant | £10k
Delivery | Buidling foundations | 2020-08-01 | 2 weeks | Lay foundations | Foundations complete | Cement | 25000 | 6 week order time for cement